## Sprint i
ID | User Story | Task ID | Story Tasks | Sprint Number | Sprint Goal | Story Type | Story Points | Story Points Completed | Names and Contribution Percentage
6 | Address feedback on D1 | 6.0 | Add priority field on product backlog | 2 | Continue developing the frontend of the app, start implementing the backend, finish SRS Documentation, establish which requirements and user stories to prioritize, and start developing them. | NF | 1 | 1 | Eric
|  | 6.1 | Add estimates on other fields |  |  | NF | 1 | 1 | Eric
|  | 6.3 | Add Quality Checking Policy to GitHub wiki |  |  | NF | 1 | 1 | Eric
|  | 6.4 | Address feedback on Requirements in SRS Document |  |  | NF | 2 | 2 | Team 25% each
7 | Set up the backend of the app | 7.0 | Create an account database |  |  | F | 5 | 5 | Josh and Siddhartha 50% each
|  | 7.1 | Choose a backend and set up the system |  |  | F | 5 | 3 | Saurav
|  | 7.2 | Connect login interface to account database |  |  | F | 2 | 2 | Josh
|  | 7.3 | Connect accounts creation window to accounts database |  |  | F | 3 | 0
8 | Set up the frontend of the app | 8.0 | Create a user login interface |  |  | F | 2 | 2 | Josh 80% and Siddhartha 20%
|  | 8.1 | Set up a account creation interface |  |  | F | 1 | 1 | Siddhartha
|  | 8.2 | Update build environment and necessary dependencies |  |  | F | 1 | 1 | Josh
9 | Update Documentation | 9.0 | Update Sprint Backlog |  |  | NF | 1 | 1 | Saurav
|  | 9.1 | Update Product Backlog |  |  | NF | 1 | 1 | Eric
|  | 9.2 | Make changes to README on GitHub |  |  | NF | 1 | 1 | Josh
|  | 9.3 | Fill up the remaining parts of SRS Document |  |  | NF | 8 | 8 | Team 25% each
10 | Create design elements | 10.0 | Decide on user stories to implement |  |  | NF | 1 | 1 | Eric
|  | 10.1 | Create 4 use cases and 1 use case diagram (each) |  |  | NF | 3 | 2 | Team 25% each
|  | 10.2 | Update UI Mockups |  |  | F | 3 | 3 | Saurav
|  | 10.3 | Create Spreadsheet mockups |  |  | F | 3 | 3 | Eric
|  | 10.4 | Test Spreadsheet mockups |  |  | F | 2 | 0
|  | 10.5 | Test Prior Solutions |  |  | NF | 2 | 2 | Josh, Saurav, Siddhartha

## Column Description
o Sprint Goal and Number. o Story copied from the project backlog or a sprint task story. o Story Type: F (functional), NF (non-functional) with a subtype: B (bug), T (technical work), KA(knowledge acquisition, technical or design/users). o Story Points. o Story Points Completed. o Team Member Names and percentage of contribution to the story.