## Sprint i
ID | User Story | Task ID | Story Tasks | Sprint Number | Sprint Goal | Story Type | Story Points | Story Points Completed | Names and Contribution Percentage
117 | Update Documentation | 117.0 | Update Detailed Design Document | 5 | Make a few improvements from D4. Refactor code and clean up any issues following the refactor. Also added more tests for features | NF | 2 | 1 | Siddhartha
|  | 117.1 | Update Sprint Backlog |  |  | NF | 1 | 1 | Siddhartha
|  | 117.2 | Update Product Backlog |  |  | NF | 1 | 1 | Josh, Siddhartha
|  | 117.3 | Upload docs to GitHub |  |  | NF | 1 | 1
|  | 117.4 | Update contribution percentage doc |  |  | NF | 1 | 1 | Team
|  | 117.5 | Record Video |  |  | NF | 3 | 3 | Team
118 | Refactor homepage code | 118.0 | Breakdown homepage.js into multiple components |  |  | F | 5 | 3 | Eric, Josh
|  | 118.1 | Test features after refactor |  |  | F | 4 | 4 | Team
|  | 118.2 | Improve Naming Conventions |  |  | F | 2 | 1 | Eric
119 | Write and update tests | 119.0 | Write test for tutorial |  |  | F | 2 | 2 | Josh
|  | 119.1 | Write test for transaction history |  |  | F | 2 | 2 | Saurav
|  | 119.2 | Write test for budget dashboard |  |  | F | 2 | 2 | Eric
|  | 119.3 | Write test for Update Categories |  |  | F | 2 | 2 | Siddhartha
|  | 119.4 | Refactor the existing tests |  |  | F | 3 | 3 | Eric
120 | Address feedback from D4 | 119.0 | Address Comments in domain model |  |  | NF | 1 | 1 | Siddhartha
121 | Update and implement more features | 120.0 | Incorporate transaction history |  |  | F | 3 | 3 | Saurav
|  | 120.1 | Fix log transaction |  |  | F | 3 | 3 | Saurav
|  | 120.2 | Category breakdown added |  |  | F | 2 | 2 | Saurav
|  | 120.3 |  |  |  | F
122 | Improve Pie Chart functionality | 121.0 | Added Nested Pi Functionaity |  |  | F | 2 | 2 | Eric

## Column Description
o Sprint Goal and Number. o Story copied from the project backlog or a sprint task story. o Story Type: F (functional), NF (non-functional) with a subtype: B (bug), T (technical work), KA(knowledge acquisition, technical or design/users). o Story Points. o Story Points Completed. o Team Member Names and percentage of contribution to the story.