## Sprint i
ID | User Story | Task ID | Story Tasks | Sprint Number | Sprint Goal | Story Type | Story Points | Story Points Completed | Names and Contribution Percentage
1 | Update Project Description Document | 1.0 | Edit the previous descriptions based on feedback | 1 | Set up documentation, establish requirements, respond to comments, and set up UI Design and Build Environment. | NF | 1 | 1 | Team 25% each
|  | 1.1 | Respond to feedback comment |  |  | NF | 2 | 2 | Team 25% each
2 | Update User Stories Document | 2.0 | Edit the previous user stories based on feedback |  |  | NF | 1 | 1 | Team 25% each
|  | 2.1 | Respond to feedback comment |  |  | NF | 2 | 2 | Team 25% each
3 | Prepare Zenhub/Kanban | 3.0 | Make sure Sprint Backlog and Product Backlog match |  |  | NF | 1 | 1 | Team 25% each
|  | 3.1 | Make sure all user stories are in product backlog |  |  | NF | 1 | 1 | Siddhartha 80%, 20% Saurav
|  | 3.2 | Add stories worked on Deliverable 1 |  |  | NF | 1 | 1 | Saurav
|  | 3.3 | Make sure Sprint Backlog reflects Product Backlog |  |  | NF | 1 | 1 | Team
|  | 3.4 | Add story tasks worked on Deliverable 1 |  |  | NF | 1 | 1 | Saurav
|  | 3.5 | Make Kanban board on GitHub |  |  | NF | 2 | 2 | Eric 40% Josh 60%
4 | Prepare Requirements | 4.0 | Come up with 10-15 Non-Functional Requirements |  |  | NF | 1 | 1 | Team 25% each
|  | 4.1 | Come up with 15-30 Functional Requirements |  |  | NF | 1 | 1 | Team 25% each
|  | 4.2 | Put the requirements with associated parts of SRS Document |  |  | NF | 2 | 2 | Team 25% each
5 | Set up Build Environment | 5.0 | Have some sort of code/HTML in GitHub |  |  | F | 3 | 3 | Josh
|  | 5.1 | Add information on installation & build process on README |  |  | NF | 1 | 1 | Eric 90%, Josh 10%
|  | 5.2 | Upload Screenshot of App running on everyone's machine |  |  | F | 1 | 1 | Team
|  | 5.3 | Design Visual Mockups |  |  | F | 3 | 3 | Eric

## Column Description
o Sprint Goal and Number. o Story copied from the project backlog or a sprint task story. o Story Type: F (functional), NF (non-functional) with a subtype: B (bug), T (technical work), KA(knowledge acquisition, technical or design/users). o Story Points. o Story Points Completed. o Team Member Names and percentage of contribution to the story.