## Sprint i
ID | User Story | Task ID | Story Tasks | Sprint Number | Sprint Goal | Story Type | Story Points | Story Points Completed | Names and Contribution Percentage
114 | Update Documentation | 114.0 | Update Detailed Design Document | 4 | Implement more tests into our application, Work on the Detailed Design Document, add more general features and polish out existing features of our app | NF | 3 | 3
|  | 114.1 | Update Sprint Backlog |  |  | NF | 1 | 1 | Saurav
|  | 114.2 | Update Product Backlog |  |  | NF | 1 | 1 | Saurav
|  | 114.3 | Upload docs to GitHub |  |  | NF | 1 | 1 | Sid
|  | 114.4 | Update contribution percentage doc |  |  | NF | 1 | 1 | Team, 25% each
|  | 114.5 | Record Video |  |  | NF | 3 | 3 | Saurav, Eric 50% each
115 | Add more features to app | 115.0 | Add Clear Data |  |  | F | 2 | 2 | Eric
|  | 115.1 | Add Log Out |  |  | F | 2 | 2 | Saurav
|  | 115.2 | Add Delete Account |  |  | F | 2 | 2 | Saurav
|  | 115.3 | Add Log Transaction |  |  | F | 4 | 3 | Saurav
|  | 115.4 | Implement Tutorial |  |  | F | 2 | 2 | Eric
|  | 115.6 | Update pie chart |  |  | F | 2 | 2 | Josh 55% Siddhartha 20% Eric 15%
116 | Implement Tests | 116.0 | Add tests for logout |  |  | F | 2 | 2 | Josh
|  | 116.1 | Add tests for homepage |  |  | F | 4 | 4 | Eric
|  | 116.2 | Add tests for login |  |  | F | 2 | 2 | Eric

## Column Description
o Sprint Goal and Number. o Story copied from the project backlog or a sprint task story. o Story Type: F (functional), NF (non-functional) with a subtype: B (bug), T (technical work), KA(knowledge acquisition, technical or design/users). o Story Points. o Story Points Completed. o Team Member Names and percentage of contribution to the story.