## Sheet1
See column descriptions in other tab
ID | User Story | Sprint Number | Story Priority | Story Status | Story Points
101 | Update Project Description Document | 1 | M | D | 1
102 | Update User Stories Document |  | M | D | 1
103 | Prepare Zenhub/Kanban |  | H | D | 2
104 | Prepare Requirements |  | M | D | 1
105 | Set up Build Environment |  | H | D | 3
6 | As a user, I want to be able to set my own spending categories so that I can know what I’m saving my money for and be motivated. |  | H | W | 3
7 | As a user, I want to know that my data is secure so that malicious actors can’t access it. | 2 | M | W | 1
8 | As a user who’s new to budgeting, I want to see common budgeting ratios so I can begin saving effectively. |  | L | W | 2
9 | As a user, I want a way to compare my budgeting habits with other platform users so that I can improve my process. |  | L | W | 8
10 | As a busy person, I want to be able to access the site quickly so that I can log purchases or check my budget during the day. |  | M | W | 2
11 | As a user, I want to see a visual representation of my budget so I can better understand my spending habits. |  | H | W | 5
12 | As a traveler, I want the ability to see my budget in different currencies so I can easily manage my budget in another country. |  | L | W | 1
13 | As a user, I want the ability to export my transaction data so I can keep records of my finances. |  | L | W | 1
14 | As a user, I want to enter my income into the system so I know how much money I have to work with. |  | H | W | 1
15 | As a user, I want to set spending limits each month to aid in keeping me within my budget. |  | H | W | 2
16 | As a user, I want to be able to import or log my transactions effortlessly so that I can overcome the common barrier to starting and maintaining my budget. |  | H | W | 3
17 | As a student, I want to be able to receive notifications if I’m approaching my spending limits so that I can adjust my expenses. |  | H | W | 5
18 | As a student, I want to be able to get an overview of my spending during the semester so that I can analyze my spending and plan better for future semesters. |  | M | W | 2
19 | As a roommate, I want an easy way to split costs between me and my roommate so that we can fairly manage our finances. |  | L | W | 3
20 | As a user, I want to be able to sync my bank accounts automatically so that I don’t have to manually enter transactions. |  | M | W | 13
21 | As a person with a joint bank-account, I want precise budgeting recommendations, so that one person is not out-spending their budget at the expense of their co account-holder. |  | M | W | 8
22 | As a user with an irregular income, I want cash-flow predictions so that I can properly budget my money for months with low income. |  | M | W | 3
23 | As a user, I want a way to see upcoming bills, so that I don’t miss a payment. |  | M | W | 1
24 | As a user, I want to receive recommendations for trimming my budget in specific categories, so I can prioritize cutting down my money on non-essential categories. |  | L | W | 8
25 | As a user, I want the ability to use this site on my phone so that I can track finances on the go. |  | M | W | 2
106 | Address feedback on D1 | 2 | M | D | 1
107 | Set up the backend of the app | 2 | H | D | 5
108 | Set up the frontend of the app | 2 | H | D | 3
109 | Update documentation | 2 | L | D | 2
110 | Create design elements | 2 | M | D | 3
111 | Update documentation | 3 | L | D | 2
112 | Continue with backend development | 3 | H | D | 4
113 | Frontend Testing/Development | 3 | H | D | 3

## Description of Columns
ID: unique # for each story * Story: Contains the user stories (one story per row) in priority order ▪ Formatted as “As a <user role>, I need to <feature needed> because of <benefit>. o Sprint: The story’s sprint number (when it gets implemented) o Story Priority: H (high), M (medium), L (low) o Story Status: W (waiting), IP (in progress), T (testing), D (done) o Story Points: Number of story points gives an indication of the difficulty of the story’s development and testing as well as possibly an estimate of the number of hours to design, implement, and test the story.