## Sprint i
ID | User Story | Task ID | Story Tasks | Sprint Number | Sprint Goal | Story Type | Story Points | Story Points Completed | Names and Contribution Percentage
111 | Update Documentation | 111.0 | Update Sprint Backlog | 3 | Add more documentation to the app, design tests, set up architecture design and domain model, respond to Dr. Greg's feedback, add more user info to backend and implment more interfaces into the app. | NF | 1 | 1 | Saurav
|  | 111.1 | Update Product Backlog |  |  | NF | 1 | 1 | Saurav
|  | 111.2 | Address Dr. Greg's comments |  |  | NF | 2 | 2 | Team, 25% each
|  | 111.3 | Modify usability testing doc |  |  | NF | 1 | 0 | NA/not required
|  | 111.4 | Continue setting up Artitecture Design |  |  | NF | 2 | 2 | Team, 25% each
|  | 111.5 | Set up domain model |  |  | NF | 3 | 3 | Eric 50%, team 16.6% each
|  | 111.6 | Document app with a recorded video showcasing features |  |  | NF | 4 | 4 | Team, 25% each
112 | Continue with backend development | 112.0 | Connect manual log in to DB |  |  | F | 2 | 2 | Eric 10%, Josh 90%
|  | 112.1 | Connect account creation to DB |  |  | F | 2 | 2 | Eric 10%, Saurav 80%, Siddhartha 10%
|  | 112.2 | Start connecting other user info to DB |  |  | F | 3 | 3 | Siddhartha
|  | 112.3 | Deal with Dr. Greg's nefarious commit |  |  | F | 3 | 3 | Eric 75%, Josh 25%
113 | Frontend Testing/Development | 113.0 | Write automated tests |  |  | F | 3 | 3 | Eric 80%, Josh 20%
|  | 113.1 | Research & Set up graphical visualization tool |  |  | F | 2 | 1 | Josh 95%, Saurav 5%
|  | 113.2 | Implement more interfaces from UI mockup to app |  |  | F | 3 | 0 | Siddhartha

## Column Description
o Sprint Goal and Number. o Story copied from the project backlog or a sprint task story. o Story Type: F (functional), NF (non-functional) with a subtype: B (bug), T (technical work), KA(knowledge acquisition, technical or design/users). o Story Points. o Story Points Completed. o Team Member Names and percentage of contribution to the story.